## To-do list
Principal Gift Strategy meetings Action Item Tracker |  |  |  |  | Not Started | 1 | In Progress | 1
[5 empty] | Deferred | 1 | Complete | 5
Task | Priority | Action Item Assigned To | Status | Start date | Due date | Completed Date | % Complete | Done/Overdue? | Notes
1.0 John Smith - VP connect with former BOT to see if she can facilitate conversation with them | Normal | Joe | Complete | 2023-08-14 | 2023-08-23 | 2024-02-27 | 100% | 1 | Pres. doesn't have relationship, John has health issues. Former BOT will be here for Antiques Forum Feb 2024. Joe will email in advance - done 2.15.24 Per former BOT's response to Joe, their connection to John Smith is thin - via a mutual acquantaince that lives near the them
2.1 Robert Brown - do the Johnsons know him? Paul to ask | Normal | Paul | Complete | 2023-08-14 | 2023-09-13 | 2023-08-17 | 100% | 1 | Paul exchanged e-mails with Johnsons, who responded that Browns have a home in their neighborhood, but they do no know them.
2.2 Robert Brown - Lindsay to assign Julie as Secondary Manager due to prospect's add'l Florida property | Normal | Lindsay | Complete | 2023-08-14 | 2023-08-15 | 2023-08-14 | 100% | 1
2.3 Robert Brown - Joe suggested sending him ginger cakes with a handwritten note from Pres. | Normal | Julie | Not Started | 2023-08-14 | 2023-09-13 |  | 0% | 0 | Julie will add him to April list for Pres. handwritten notes
2.4 Robert Brown - Julie suggested writing a profile piece for Trend & Tradition to recognize her years of giving | Normal | Julie | Deferred | 2023-08-14
3.1 Susan Moore - Ken reach out to Rob Jones who's in the telecoms industry, can we make a connection to Moore thru him? | Normal | Ken | Complete | 2023-07-10 | 2023-08-09 |  | 100% | 1 | Rob Jones said he did not know her
3.2 Susan Moore - make sure she is on prospect/invitation list to the campaign event in Charlottesville in 2024 | Normal | Lindsay | Complete | 2023-07-10 | 2024-06-30 | 2024-06-20 | 100% | 1 | 6.5.2024 - LR currently working on C'ville list refresh
3.3 Susan Moore - Joe will see Bruce this week, will ask if he recognizes Moore's name, perhaps can help with connection | Normal | Joe | In Progress | 2023-07-10 | 2023-08-09 |  | 50% | 0
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
[7 empty] | 0% | -1
Formulas:
Due date = ToDoList2[[#This Row],[Start date ]]+9